## README
Last Update | 2019-04-22
Author | Daniel D'Orange / Jerry Tan / Brett Korp / James Kwon
Email | ddor001@ucr.edu / jtan027@ucr.edu / bkorp001@ucr.edu / jkwon022@ucr.edu
Description | This is the Scrum Document for the SyncTheatre team in CS180. This document reflects the progress and state of the SyncTheatre web app.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Change video queue to horizontal (Daniel/Jerry) |  |  | Setup React App (Jerry)
Add Arrows, Play Button, and Remove button (Jerry) |  |  | Rooms Routes (Brett)
Display Title, Video Length on Video Queue (Jerry) |  |  | WebSocket Routes (Brett)
Modify Video Info route to include video length (Brett) |  |  | Video Routes (James)
on vid queue change PUT to /api/rooms/queue/:id (Jerry) |  |  | Sync Control Library (Brett)
Add PUT /api/rooms/queue/:id route (James) |  |  | Room Page (Jerry)
Only Allow controls to modify queue if party leader (Brett/Jerry) |  |  | Home Page (Jerry)
Add theatre mode button (Daniel) |  |  | Login Page (Jerry)
Toggle video layout between theatre/normal mode (Daniel) |  |  | add users tab to chat component (Jerry/Daniel)
Synchronization Algorithm (Daniel/Brett) |  |  | Modify room to move queue below vid (Jerry/Daniel)
Enable synch tick on front-end lib (Brett) |  |  | Add a create registered user route (Brett)
Add way to get latency for each client (Brett) |  |  | Add chat functionality to chat component (Brett)
Add Profile Page (Jerry) |  |  | Add chat event handlers to sync-lib (Brett)
Edit user name on profile page (James) |  |  | Add chat message event (Brett)
Add user joined room event (Brett)
Additional |  |  | Add Room Users component (Brett)
Add auth middleware to protected routes ( Brett) |  |  | Add get all users in room route (Brett)
UI dark theme + overhaul |  |  | Add roomName to registered User (Brett)
Add Persistent URL Room Routes to front-end (Brett)
Bugs |  |  | Add layout to chat component (Daniel/Jerry)
User list sometimes not rendering on first user joining |  |  | Add UserOptions component to users tab (Brett)
no way to control room when a party leader leaves temp room |  |  | On sign-in update userID in session storage (Daniel)
delete old temporary rooms after 10 mins |  |  | Add Sign In Button to login page (Daniel)
delete old temporary user accounts after 10 mins
When in room, click home then click back - multi users in room
Abuse home back bug, then change party leader => crash

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Login | As a person interested in using SyncTheatre, I want to create an account so that I can login and logout. | 5 | 3 | 2nd Sprint Done
2 | Room | As a user on SyncTheatre, I want to be able to create a room where all users are kept within 0.5 seconds of each other on the same video so that the video is synchronized. | 5 | 1 | 1st Sprint Done
3 | Persistent URLs | As a registered user on SyncTheatre, I want to have a persistent URL for my room so that I don’t have to keep sending it to my friends. | 5 | 5 | 2nd Sprint Done
4 | Party Leader | As a user on SyncTheatre, I want to be the party leader of my room and control the current timestamp of the video so that I can go back to show off something my friends missed. | 5 | 2 | 1St Sprint Done
5 | Change Party Leader | As a user on SyncTheatre, I want to give someone else in the room the party leader status so that they can keep things going while I get snacks. | 5 | 4 | 2nd Sprint Done
6 | Video Queue for Non-Party Leaders | As a user on SyncTheatre, I want to submit videos to the video queue so that the party leader can decide whether or not to add it to the queue. | 5 | 6 | 1st Sprint Done
7 | Video Queue Manipulation | As a party leader of a room on SyncTheatre, I want to modify the the video queue to change the order of videos, delete videos, or add new videos and play any video in the queue. | 5 | 7 | 3rd Sprint Progress
8 | Chat | As a user on SyncTheatre, I want to be able to use the chat on the website so that I can communicate with my friends without using an external program. | 5 | 8 | 2nd Sprint Done | .
9 | Theatre Mode | As a user on SyncTheatre, I want to be able to enlarge the video by going into 'Theatre Mode'. In Theat're mode chat and the video queue are not the focus | 5 | 9 | 3rd Sprint Progress
10 | Real Time Synchronization | As a user if I deviate from the party leader's playback while watching a video I want to be synchronized with the real-time playback of the party leader | 5 | 10 | 3rd Sprint Progress
11 | User Profile | As a user I want to be able to see a profile page for my user account so that I can view my user name and other user information. | 5 | 11 | 3rd Sprint Progress
| Total |  | 45

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | David Hoffman | Task ?

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 2 | 2 | 33 | 30.625
2 | 36 | 3 | 5 | 31 | 26.25
3 | 36 | 3 | 8 | 28 | 21.875
4 | 36 | 4 | 12 | 24 | 17.5
5 | 34 | 3 | 15 | 19 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0