## README
Last Update | 2019-04-22
Author | Daniel D'Orange / Jerry Tan / Brett Korp / James Kwon
Email | ddor001@ucr.edu / jtan027@ucr.edu / bkorp001@ucr.edu / jkwon022@ucr.edu
Description | This is the Scrum Document for the SyncTheatre team in CS180. This document reflects the progress and state of the SyncTheatre web app.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
WebSocket Routes (Brett) | Home Page (Jerry)
Sync Control Library (Brett) | Room Page (Jerry)
Setup React App (Jerry) | Login Page (Jerry)
Synchronization Algorithm (Daniel) | Registration Page (Jerry)
Authentication Routes (Daniel)
Rooms Routes (Brett)
Video Routes (James)

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Login | As a person interested in using SyncTheatre, I want to create an account so that I can login and logout. | 5 | 3
2 | Room | As a user on SyncTheatre, I want to be able to create a room where all users are kept within 0.5 seconds of each other on the same video so that the video is synchronized. | 5 | 1
3 | Persistent URLs | As a registered user on SyncTheatre, I want to have a persistent URL for my room so that I don’t have to keep sending it to my friends. | 5 | 5
4 | Party Leader | As a user on SyncTheatre, I want to be the party leader of my room and control the current timestamp of the video so that I can go back to show off something my friends missed. | 5 | 2
5 | Change Party Leader | As a user on SyncTheatre, I want to give someone else in the room the party leader status so that they can keep things going while I get snacks. | 5 | 4
6 | Video Queue for Non-Party Leaders | As a user on SyncTheatre, I want to submit videos to the video queue so that the party leader can decide whether or not to add it to the queue. | 5 | 6
7 | Video Queue Manipulation | As a party leader of a room on SyncTheatre, I want to modify the the video queue to change the order of videos, delete videos, or add new videos. | 5 | 7
8 | Chat | As a user on SyncTheatre, I want to be able to use the chat on the website so that I can communicate with my friends without using an external program. | 5 | 8 |  | .
9 | Forgot my Password | As a registered user on SyncTheatre, I want to be able to reset my password if I forget it so that I don’t lose access to my account. | 5 | 9
| Total |  | 45

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 | David Hoffman | Task ?

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 35 | 0 | 0 | 35 | 35
1 | 35 | 2 | 2 | 33 | 30.625
2 | 36 | 3 | 5 | 31 | 26.25
3 | 36 | 3 | 8 | 28 | 21.875
4 | 36 | 4 | 12 | 24 | 17.5
5 | 34 | 3 | 15 | 19 | 13.125
6 |  |  |  |  | 8.75
7 |  |  |  |  | 4.375
8 |  |  |  |  | 0